## BONUS
LogDate | EmpID | Category | BonusHour | Remarks
2019-02-14 | 5099223 | Company | 1 | No Punching Machine at site- Asst. Safety Officer
2019-02-16 | 5099223 | Company | 1 | No Punching Machine at site- Asst. Safety Officer
2019-02-17 | 5099223 | Company | 1 | Site - Asst. Safety Officer
2019-02-18 | 5099223 | Company | 1 | Site - Asst. Safety Officer
2019-02-19 | 5099223 | Company | 1 | Site - Asst. Safety Officer
2019-02-19 | 5033920 | Company | 1 | Pile rubish shifting sand leveling
2019-02-19 | 5036124 | Company | 1 | Pile rubish shifting sand leveling
2019-02-20 | 5099223 | Company | 1 | Site - Asst. Safety Officer
2019-02-23 | 5099223 | Company | 1 | Site - Asst. Safety Officer
2019-02-24 | 5099223 | Company | 1 | Site - Asst. Safety Officer
2019-02-24 | 5088433 | Company | 1 | Sign board making
2019-02-24 | 5088435 | Company | 1 | Sign board making
2019-02-17 | 5088433 | Company | 1 | Sign board making
2019-02-17 | 5088435 | Company | 1 | Sign board making
2019-02-18 | 5088433 | Company | 1 | Sign board making
2019-02-18 | 5088435 | Company | 1 | Sign board making
2019-02-21 | 5088433 | Company | 1 | Sign board making
2019-02-21 | 5088435 | Company | 1 | Sign board making
2019-02-23 | 5088433 | Company | 1 | Sign board making
2019-02-23 | 5088435 | Company | 1 | Sign board making
2019-02-25 | 5036124 | Company | 1 | Pile area backfilling & leveling work
2019-02-25 | 5033920 | Company | 1 | Pile area backfilling & leveling work
2019-02-25 | 5011863 | Company | 1 | Pile area backfilling & leveling work
2019-02-25 | 5088433 | Company | 1 | Sign board making
2019-02-25 | 5088435 | Company | 1 | Sign board making
2019-02-25 | 5099223 | Company | 1 | Site -Safety Officer
2019-02-25 | 2077016 | Company | 1 | Site work
2019-02-26 | 5036124 | Company | 2 | PCC Preparation & Casting
2019-02-26 | 5025585 | Company | 2 | PCC Preparation & Casting
2019-02-26 | 5011863 | Company | 2 | PCC Preparation & Casting
2019-02-26 | 5011866 | Company | 2 | PCC Preparation & Casting
2019-02-26 | 5099223 | Company | 2 | Site Saety
2019-02-26 | 5011143 | Company | 2 | Charge in hand
2019-02-26 | 2077016 | Company | 2 | Asst. Foreman
2019-02-26 | 5088433 | Company | 1 | Sign board making
2019-02-26 | 5088435 | Company | 1 | Sign board making
2019-02-27 | 5011695 | Company | 1 | Pile area backfilling & leveling work
2019-02-27 | 5033920 | Company | 1 | Pile area backfilling & leveling work
2019-02-27 | 5036124 | Company | 1 | Pile area backfilling & leveling work
2019-02-27 | 5022811 | Company | 1 | Pile area backfilling & leveling work
2019-02-27 | 5011863 | Company | 1 | Pile area backfilling & leveling work
2019-02-27 | 5088433 | Company | 1 | Sign board making
2019-02-27 | 5099223 | Company | 1 | Site Saety
2019-02-27 | 5011143 | Company | 1 | Charge in hand
2019-02-27 | 2077016 | Company | 1 | Asst. Foreman
2019-02-27 | 2002086 | Company | 1 | Mobile crane Operator
2019-02-27 | 5044823 | Company | 1 | Mobile crane Rigger
2019-02-28 | 5025585 | Company | 2 | Shoring Panel fixing
2019-02-28 | 5022811 | Company | 2 | Shoring Panel fixing
2019-02-28 | 5011866 | Company | 2 | Pile area backfilling & leveling work
2019-02-28 | 5033920 | Company | 2 | Pile area backfilling & leveling work
2019-02-28 | 5011863 | Company | 2 | Pile area backfilling & leveling work
2019-02-28 | 5099223 | Company | 2 | Site Saety
2019-02-28 | 5011143 | Company | 2 | Charge in hand
2019-02-28 | 2077016 | Company | 2 | Asst. Foreman

## ATTEND
USERID | PunchDate | PunchIn | PunchOUT | REMARKS | workLocation | Category | SubCategory | ShiftDesc
5036067 | 2018-07-01 | 0:10 | 11:00 | Concrete casting for water tank and Net column and finishing work | P-163 | Company |  | 2 Days Cont. Shift
5022626 | 2018-07-01 | 5:00 | 19:00 | Concrete casting for water tank and Net column and finishing work | P-163 | Company |  | SUM 5AM TO 11AM
5033523 | 2018-07-01 | 5:00 | 19:00 | Concrete casting for water tank and Net column and finishing work | P-163 | Company |  | SUM 5AM TO 11AM
2002204 | 2018-07-01 | 5:00 | 19:00 | Card not available (JCB operator) JCB out of order | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-02 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
2002204 | 2018-07-02 | 5:00 | 19:00 | Card not available (JCB operator) JCB out of order | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-03 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
2002205 | 2018-07-03 | 5:00 | 17:00 | Forget Punch out | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-04 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5074020 | 2018-07-04 | 5:00 | 19:00 | Forget Punch out | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-05 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5011152 | 2018-07-06 | 6:00 | 11:00 | Closing shuttering in water tank wall | P-163 | Subcontractor | 5011141
5022407 | 2018-07-06 | 6:00 | 11:00 | Closing shuttering in water tank wall | P-163 | Subcontractor | 5011141
5011755 | 2018-07-06 | 6:00 | 11:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755
5011577 | 2018-07-07 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5011152 | 2018-07-07 | 5:00 | 19:00 | Closing shuttering in water tank wall | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011592 | 2018-07-07 | 5:00 | 19:00 | Closing shuttering in water tank wall | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011827 | 2018-07-07 | 5:00 | 19:00 | Closing shuttering in water tank wall | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5022407 | 2018-07-07 | 5:00 | 19:00 | Closing shuttering in water tank wall | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011755 | 2018-07-08 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5011755 | 2018-07-09 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5011152 | 2018-07-09 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011592 | 2018-07-09 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011827 | 2018-07-09 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5022407 | 2018-07-09 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5025516 | 2018-07-09 | 19:00 | 5:00 | punching card forget | P-163 | Subcontractor | 5022266 | 163-NT-7PM
5011755 | 2018-07-10 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5011152 | 2018-07-10 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011592 | 2018-07-10 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011827 | 2018-07-10 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5022407 | 2018-07-10 | 5:00 | 19:00 | water tank slab scafolding work and shutter removing returning wall in water tank | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5044864 | 2018-07-10 | 5:00 | 19:00 | Forget Punch out | P-163 | Company |  | SUM 5AM TO 11AM
5044864 | 2018-07-10 | 5:00 | 19:00 | Forget Punch out | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-11 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5044864 | 2018-07-11 | 5:00 | 19:00 | Punching card loss | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-12 | 5:00 | 19:00 | Block work in holding tank area | P-163 | Subcontractor | 5011755 | SUM 5AM TO 11AM
5044864 | 2018-07-12 | 5:00 | 19:00 | Punching card loss | P-163 | Company |  | SUM 5AM TO 11AM
5011755 | 2018-07-14 | 16:00 | 23:50 | Forget punch out (concrete casting for water tank and tie beam) | P-163 | Company |  | SUM 5AM TO 11AM
5022626 | 2018-07-14 | 5:00 | 21:30 | concrete casting for water tank and tie beam | P-163 | Company |  | SUM 5AM TO 11AM
5022626 | 2018-07-15 | 5:00 | 19:00 | Matterial arrengment and house keeping | P-163 | Company |  | SUM 5AM TO 11AM
5044909 | 2018-07-15 | 5:00 | 19:00 | Water tank area prepration work | P-163 | Company |  | SUM 5AM TO 11AM
5036067 | 2018-07-15 | 5:00 | 19:00 | Shutter fixing for tie beam and pcc leveling | P-163 | Company |  | SUM 5AM TO 11AM
5022626 | 2018-07-16 | 5:00 | 19:00 | (Work as a Subcontractor punching card not replaced) Spacer making | P-163 | Company |  | SUM 5AM TO 11AM
5036067 | 2018-07-16 | 5:00 | 23:50 | (Work as a Subcontractor punching card not replaced) Shutter making for pcc and concrete casting for Holding tank and finishing | P-163 | Company |  | SUM 5AM TO 11AM
5033523 | 2018-07-16 | 5:00 | 19:00 | (Work as a Subcontractor punching card not replaced) water stopper fixing for holding tank | P-163 | Company |  | SUM 5AM TO 11AM
5036067 | 2018-07-17 | 0:10 | 5:00 | concrete casting for holding tank and finishing work | P-163 | Company |  | 2 Days Cont. Shift
5011895 | 2018-07-18 | 5:00 | 19:00 | Forget punch out | P-163 | Company |  | SUM 5AM TO 11AM
5011856 | 2018-07-19 | 5:00 | 19:00 | Punching time error (red) show | P-163 | Company |  | SUM 5AM TO 11AM
5011610 | 2018-07-19 | 5:00 | 16:00 | Forget punch out (shutter closing for holding tank returning wall and tie beam) | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM
5011610 | 2018-07-20 | 6:00 | 11:00 | New card not activated (shutter removing for holding tank returning wall and tie beam) | P-163 | Subcontractor | 5011141
5011610 | 2018-07-21 | 5:00 | 19:00 | New card not activated (shutter closing for tie beam) | P-163 | Subcontractor | 5011141 | SUM 5AM TO 11AM